## Sheet1
| 2026-06-01 |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Scoping – Plan
Scoping – Actual | bar: 2026-06-01 W1
Requirement – Plan | bar: 2026-06-01 W1 to 2026-06-01 W4
Requirement – Actual | bar: 2026-06-01 W2 to 2026-08-01 W1
Design – Plan | bar: 2026-08-01 W1 to 2026-09-01 W4
Design – Actual | bar: 2026-08-01 W1 to 2026-09-01 W4
Development & SIT – Plan | bar: 2026-08-01 W4 to 2026-09-01 W4
Development & SIT – Actual | bar: 2026-08-01 W4 to 2026-10-01 W1
UAT – Plan | bar: 2026-10-01 W1 to 2026-10-01 W2
UAT – Actual | bar: 2026-09-01 W4
Rollout / Go-Live – Plan | bar: 2026-10-01 W3 to 2026-10-01 W4
Rollout / Go-Live – Actual | bar: 2026-09-01 W4
1 pillar = 1 report = 1 screen
Note on K7: Requirement Gathering & Validation completed: BRS v3.2 reviewed and validated against Q1 2026 board decks; BRS Walkthrough held 6 Aug 2026.
Note on K9: Design work has been continuous since Aug W1, including a round of iteration through the Sept UAT cycle. Formal design sign-off (Milestone M2) is still pending as of 29 Sept 2026 — this bar shows elapsed effort, not completion.
Note on N11: Development is substantially complete (all 19 screens live on Supabase/Postgres; maker-checker Verify & Publish extended to Financial Health/Resource & People; go-live data cutover done 28 Sept 2026). System Integration Testing has not yet started — this bar reflects Development progress only.
Note on R13: UAT Round 1 conducted 22-24 Sept 2026 with 5 participants against Test Script Masterlist v3; 9 bugs found and closed out. Pulled forward from the originally planned Oct W1-W2 window. Round 2 to be scheduled.
Note on R15: Go-live data cutover completed 28 Sept 2026 (pre-launch FY2025 data hidden from all pickers) in preparation for production release. This is a preparatory step only — formal deployment/go-live date is not yet confirmed, so this is marked partial, not complete.

## Change Log
Version | Date | Author | Description
1.0 | 28 August 2026 | Ahmad Najmi | Initial progress report — August 2026 claim support
1.1 | 29 September 2026 | Ahmad Najmi | September 2026 progress update — claim support
1.2 | 29 September 2026 | Ahmad Najmi | Aligned report with updated Project Timeline tracker (UAT and Rollout data cutover pulled forward)
1.3 | 29 September 2026 | Ahmad Najmi | Documented the post-go-live production data-quality audit and corrections across all three pillars, and the new upload file-download feature
1.4 | 29 September 2026 | Ahmad Najmi | Fixed a display bug where the PBT/Cost-to-Income Ratio income-statement breakdown always showed the latest quarter's figures regardless of the period selected, and added unit/decimal-convention remarks to the Data Entry Excel template's “Displayed on Dashboard” column
1.5 | 30 September 2026 | Ahmad Najmi | Corrected several Financial Health figures raised in client review of the Q2 FY2026 exhibits — a missing one-off bonus-provision reversal line, a mislabelled Profit After Tax figure, a budget dividend entry error, and a duplicated revenue budget line — and revised the Statement of Financial Position’s comparative basis to the prior financial year-end per standard reporting convention; aligned the Related Party Transactions and Actual vs Budget table layouts with the client’s own report format; restricted the login Entity selector to Prokhas only; removed the staging-environment banner; and rejected a stale test data-upload batch that would otherwise have overwritten the corrected figures once approved
1.6 | 30 September 2026 | Ahmad Najmi | Updated the Progress Against Agreed Timeline table — UI/UX & Technical Design and User Acceptance Testing marked Completed (UAT closed out within one week, design sign-off obtained), System Integration Testing moved to In Progress, and Deployment & Go-Live marked Completed in the staging environment with an SSL/HTTPS certificate configured; realigned the Summary, Milestone Status and Next Steps sections to match. Project Timeline tracker updated to match: Rollout / Go-Live actual bar marked complete (staging), Development & SIT actual bar extended into October to reflect SIT continuing in progress.