## Timesheet
CONTRACT ASSOCIATE TIME SHEET
FOR THE MONTH OF OCTOBER 2026
|  | NAME | : | Ahmad Najmi bin Ariffin
|  | DEPT / DIVISION | :
No. | DATE | TIME |  | NO. OF
|  | FROM | TO | HOURS | TYPES OF DUTIES
1 | 2026-10-01 | 9:05 | 13:50 | 4.75 | Authentication: reviewed requirements, planned Supabase Auth architecture
2 | 2026-10-02 | 12:25 | 14:25 | 2 | Authentication: implemented username/password login
3 | 2026-10-05 | 9:45 | 12:15 | 2.5 | Authentication: built forced password-change and reset-password flow
4 | 2026-10-06 | 9:10 | 11:25 | 2.25 | Authentication: built admin Access Management screen
5 | 2026-10-07 | 9:00 | 12:15 | 3.25 | Authentication: added access-matrix role; seeded user accounts
6 | 2026-10-08 | 12:25 | 17:10 | 4.75 | Authentication: end-to-end testing; deployed to production
7 | 2026-10-09 | 8:55 | 13:25 | 4.5 | Fixed Financial Results (QoQ) display crash; verified live
8 | 2026-10-12 | 10:45 | 12:45 | 2 | Excel template audit: Corporate Performance screens
9 | 2026-10-13 | 8:35 | 9:35 | 1 | Excel template audit: Financial Health & Resource and People screens
10 | 2026-10-14 | 9:35 | 11:35 | 2 | Closed Excel template coverage gaps (Highlights, Variance Commentary)
11 | 2026-10-15 | 11:10 | 13:25 | 2.25 | Designed upload "customize queue" — schema and parser logic
12 | 2026-10-16 | 8:35 | 11:35 | 3 | Built "customize queue" review UI on Verify & Publish
13 | 2026-10-19 | 9:30 | 12:30 | 3 | Investigated client query on Q3 FY2026 default-period behaviour
14 | 2026-10-20 | 11:55 | 16:40 | 4.75 | Fixed Site Usage analytics production error; verified live
15 | 2026-10-21 | 11:20 | 14:35 | 3.25 | Self-hosted backend: database schema design (MariaDB)
16 | 2026-10-22 | 9:40 | 13:55 | 4.25 | Self-hosted backend: REST API — authentication & user management
17 | 2026-10-23 | 11:35 | 15:50 | 4.25 | Self-hosted backend: REST API — KPI, submissions & detail data
18 | 2026-10-26 | 12:45 | 15:15 | 2.5 | Self-hosted backend: file storage & upload-handling endpoints
19 | 2026-10-27 | 8:30 | 12:00 | 3.5 | Self-hosted backend: data-migration & backup-sync scripts
20 | 2026-10-28 | 12:45 | 17:45 | 5 | Self-hosted backend: end-to-end testing and verification
21 | 2026-10-29 | 12:10 | 13:25 | 1.25 | Self-hosted backend: deployment documentation & handover package
22 | 2026-10-30 | 10:15 | 12:00 | 1.75 | Prepared October progress report & timesheet; progress meeting
23
24
25
| TOTAL NO. OF DAYS |  |  | 22
Claimant's Signature
Approved By
(Head Of Dept / Division)
Date